## Sheet1
Tasks | 2017-03-20 | 2017-03-24 | 2017-03-27 | 2017-03-31 | 2017-04-03 | 2017-04-07 | 2017-04-10 | 2017-04-14 | 2017-04-17 | 2017-04-21 | 2017-04-24 | 2017-04-28 | 2017-05-01 | 2017-05-05 | 2017-05-08 | 2017-05-12 | 2017-05-15 | 2017-05-19 | 2017-05-22 | 2017-05-26 | 2017-05-29 | 2017-06-02 | 2017-06-05 | 2017-06-09 | 2017-06-12 | 2017-06-16 | 2017-06-19 | 2017-06-23 | 2017-06-27
Provide inteface details ( SAP Delta Interface) for 1.x | bar: 2017-03-20 to 2017-03-24
Provide inteface details ( Starcite Delta Interface) for 1.x | bar: 2017-03-20 to 2017-03-31
Requirements for 2.0 Interface - STARCITE | bar: 2017-03-20 to 2017-03-31
Requirements for 2.0 Interface - CONCUR | bar: 2017-03-20 to 2017-03-31
Requirements for 2.0 Interface - SAP
EU Full | bar: 2017-04-07 to 2017-04-10
Start EM 2.0 deploy iN EU Full | bar: 2017-04-10 to 2017-04-14
Starter Data for EU Full ( Service Providers, Venue, vendor) | bar: 2017-04-14
Complete EM 2.0 Deploy
Start testing 1.x | bar: 2017-04-17
Deliver DE Delta interface | bar: 2017-03-20 to 2017-04-28
Unit Test setting Record Type | bar: 2017-05-01
Complete Regression 1.x | bar: 2017-04-17 to 2017-06-02
Start Testing 2.0 | bar: 2017-04-17
Deliver 2.0 interfaces | bar: 2017-03-20 to 2017-05-15
Integration for Preferences, User PS | bar: 2017-05-12 to 2017-05-15
Complete 2.0 Testing | bar: 2017-04-17 to 2017-06-09
Data Prep for UFT Env | bar: 2017-04-21
Complete UFT Env Prep | bar: 2017-04-21
Complete UFT Scripts | bar: 2017-05-29 to 2017-06-02
Complete UFT | bar: 2017-06-12 to 2017-06-16
PTP | bar: 2017-06-12 to 2017-06-16
Go-Live ( UK/I & Nordics) | bar: 2017-06-19