## LOE
CORE BUILD ESTIMATES |  | Hours | Days | Months | Requirements Capture & Document | Design and Build | Unit Testing | 2 fte
Sequence
TOTAL LOE for DEV + Unit Test |  | 1120 | 140 | 4.6667 | 440 | 440 | 240 | 70
User groups (Profiles), Sharing Rules |  |  |  |  | 80 | 120 | 40
Needs | 1 |  |  |  | 80 | 80 | 40
Simple Rectype Config & Page Layouts
WBS/CC to Need Conversion (Custom code)
Validation Rules if any
Exception Activity Type Considerations
Approval Workflows By Activity Type (Market Specific)
Budget Management & Allocation (Sharing rules)
Materials Planning | 2 |  |  |  | 80 | 80 | 40
Page layouts for Materials
Validation Rules
Exception Considerations if any
Topic Simplification/Re-evaluation
Qualification/Contracting |  |  |  |  | 80 | 80 | 40
Page layouts
Validation Rules if any for Speaker Quals
Print Invitation & Print Sign-in Sheet | 7 |  |  |  | 80 | 40 | 40
OOB Product config supported templates
Approved E-mail | 7
OOB Config without RSVP/Online registration portal setup |  |  |  |  | 40 | 40 | 40
With RSVP Support configuration
KOL Contracting (Contracting) + Doc Generation Items | 4
Validation Rules
Contract object
ICF object
VMT Generation
Activity Document
Conga Templates
Contract object
ICF object
VMT
Activity Document
Conga Configuration
Echosign Templates
Echosign Configuration
Visualforce & Apex Development
Product Configuration
1 Activity type Event Configuration
2 Countries - with and without approval
Event Layouts for Event and Related Objects to support EC
Event Actions to support EC
Event Rueles to support EC
Page layout configurations
Expense Estimates and PO Simplification
iRep Configuration & Online Configuration
Integration & Testing Support
Training Support
Reporting & Analytics
IDL
Market Specific Updates
Cut Over Planning and Support (ensuring co-existence of Simplified and non-Simplified Models)
Assumptions
Market Specific - Data Model will be identical across all markets. Profile updates, Approval WF changes allowed, Page layout changes, Sharing rule changes allowed to the core. Governance needs to be estd to maintain clean CORE.
Product config time

## TEMP
Cross Border | 12 | x
Recruitment & Qualification | 3 | x
Logistics Planning/Travel | 8 | x
Activity Details | 3 | x
KOL Selection | 3 | x
Review and Approvals | 1 | x
KOL Contracting (Contracting) | 4 | x
Invitation & Attedndee response Tracking | 7 | x
Activity Execution | 9 | x
Payment Management | 10 | x
Closeout | 11 | x
Budget Management | 1 | x
HCP Portal | 14 | x
Reporting & Analytics | 13 | x
Vendor | 5 | x
Expense estimate and PO | 6 | x
Activity Document | 6 | x

## Discussed Dates
| Req Start | Req End | Dev Start | Dev End
User groups (Profiles), Sharing Rules
Needs Assessment | 2015-04-06 | 2015-04-17
Object Visibilities & FLS By profile
Need
Initiative
Budget
Need Materials
Materials
Page layouts
Need
Initiative
Budgets
Validation Rules
Exception Activity Type Considerations
Approval Workflows By Activity Type
Budget Management & Allocation
Visualforce & Apex based custom Dev
Materials Planning | 2015-04-06 | 2015-04-17
Object Visibilities & FLS By profile
Materials
Page layouts for Materials
Validation Rules
Exception Considerations if any
Visualforce & Apex based custom Dev
Recruitment & Qualification | 2015-04-08 | 2015-05-01
Object Visibilities & FLS By profile
Speaker
Vendor (Payee)
Contract
ICF
Page layouts
Speaker
Vendor (Payee)
Contract
ICF
Validation Rules for Speaker and Payee
Exception Activity Type Considerations
Approval Workflows By Activity Type
Budget Management & Allocation
Visualforce & Apex based custom Dev
Invitation & Attendee Response Tracking | 2015-05-01 | 2015-05-15
Invitations (Options 1 + 2)
Templates
Generic (speakers + save the date)
Speaker Specific
Conga Configuration
Attendee Response Tracking (Options 1 + 3)
Force.com Site
VF Page development
Apex Controller Development
Branded Domain Simulation & Tests
KOL Contracting (Contracting) + Doc Generation Items | 2015-04-08 | 2015-05-01
Validation Rules
Contract object
ICF object
VMT Generation
Activity Document
Activity Agreement
Conga Templates
Contract object
ICF object
VMT
Activity Document
Conga Configuration
Echosign Templates
Echosign Configuration
Visualforce & Apex Development
Product Configuration | 2015-04-06 | 2015-05-15
Activity Details & Execution Config
Payment Management
Closeout Config
Logistics & Travel Planning
Object field
Page layout configurations
Expense Estimates and PO
iRep Configuration
Integration & SI Support
Cross Border
Workflow Email alerts
Training on Dataloader
Minor Dataloader scripting (if required)
Notification E-mail templates
Reporting & Analytics
IDL
Market Specific Updates
Assumptions
Market Specific - Data Model will be identical across all markets. Profile updates, Approval WF changes allowed, Page layout changes, Sharing rule changes allowed to the core. Governance needs to be estd to maintain clean CORE.
Product config time