## UKI _ Benelux Deployment Plan
Weekend Task? | Task Name | Duration | Start Date | Due Date | Assigned To | Status | % Complete | Predecessors | Comments
| Enter your deadline as start and end date: | 21d | 2017-05-22 | 2017-06-11
| Sign Off for Prod Deployment | 30d | 2017-04-30 | 2017-05-29
| Traceability (not required) | 8d | 2017-05-22 | 2017-05-29 | Deepika
| UFT Business Sign-off (not required) | 11d | 2017-05-19 | 2017-05-29 | Rosa/Daniel
| UAT Summary Report (1.x + 2.0 regression) | 8d | 2017-05-22 | 2017-05-29 | Pat, Deepika
| Germany 1.x UFT Regression | 1d | 2017-05-29 | 2017-05-29 | Rosa
| CRM Regression ? | 30d | 2017-04-30 | 2017-05-29 | Pat
| Vitalize CR logged/approved | 2d | 2017-05-28 | 2017-05-29 |  |  |  |  | Only required for Interface, not EM application
| PTP Memo ? | 8d | 2017-05-22 | 2017-05-29 | Lynn/Seemesh
| Release to Production ? | 1d | 2017-05-29 | 2017-05-29 | ?
| Communication | 25d | 2017-05-22 | 2017-06-15
| Veeva to share Metadata Excel Sheet with Accenture/Sumit | 5d | 2017-05-22 | 2017-05-26 | Murugesh Naidu
| EM Germany Weekend Blackout Communication - Fri EOD to Sun EOD | 2d | 2017-06-09 | 2017-06-10 | ?
| UKI/BLX EM Go Live Communication | 1d | 2017-05-31 | 2017-05-31 | ?
| Veeva Onsite 6-11 (Sun) through week of 6/12 | 6d | 2017-06-10 | 2017-06-15
| Communicate with KAM Team on Go Live | 5d | 2017-05-22 | 2017-05-26 | Jerald/Sumit/Murugesh
| Business Go Live Comm | 5d | 2017-05-22 | 2017-05-26 | Lynn
| Licenses | 5d | 2017-05-22 | 2017-05-26
| Events Management Users | 5d | 2017-05-22 | 2017-05-26 | Michelle
| Migration - Metadata - Jun 5th - Jun 11th | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Migrate Metadata (Eclipse/VEM) | 5d | 2017-06-05 | 2017-06-09
| Enable Audit History Tracking for relevant objects (Manual step) | 5d | 2017-06-05 | 2017-06-09
| Custom Objects | 5d | 2017-06-05 | 2017-06-09
| Translations | 5d | 2017-06-05 | 2017-06-09
| Permission Sets for UKI BLX | 5d | 2017-06-05 | 2017-06-09
TRUE | Permission Sets for DE | 5d | 2017-06-05 | 2017-06-09
| Profiles for UKI BLX | 5d | 2017-06-05 | 2017-06-09
TRUE | Profiles for DE | 5d | 2017-06-05 | 2017-06-09
| Page layouts for UKI/BLX | 5d | 2017-06-05 | 2017-06-09
TRUE | Page layouts Germany | 5d | 2017-06-05 | 2017-06-09
| Triggers | 5d | 2017-06-05 | 2017-06-09
| VF Pages | 5d | 2017-06-05 | 2017-06-09
| Workflows | 5d | 2017-06-05 | 2017-06-09
| Approval Processes | 5d | 2017-06-05 | 2017-06-09
| Custom Settings Metadata | 5d | 2017-06-05 | 2017-06-09
| Email templates | 5d | 2017-06-05 | 2017-06-09
| Reports & Reporttypes | 5d | 2017-06-05 | 2017-06-09
| Weblinks (Buttons) | 5d | 2017-06-05 | 2017-06-09
| CustomLabels | 5d | 2017-06-05 | 2017-06-09
| Tabs | 5d | 2017-06-05 | 2017-06-09
| Migrate Metadata (Manual) | 5d | 2017-06-05 | 2017-06-09
| Event Config Override for Enhanced Admin UI | 5d | 2017-06-05 | 2017-06-09
TRUE | Germany Event Page Layouts
TRUE | Germany Event Attendee Page Layouts
TRUE | Germany Event Service Provider Page Layouts
TRUE | Event child page overrides | 5d | 2017-06-05 | 2017-06-09
TRUE | Permission Set Assignments for UKI + BLX | 5d | 2017-06-05 | 2017-06-09
| Custom Settings (Manual Update/Create) | 5d | 2017-06-05 | 2017-06-09
| BMSNeedToEventInheritance - Simple Event | 5d | 2017-06-05 | 2017-06-09
| Veeva Settings Org Level and ALL UKI+BLX Profiles | 5d | 2017-06-05 | 2017-06-09
Event Management Settings
| Migration - Data | 7d | 2017-06-05 | 2017-06-11
| Plant Code ? | 5d | 2017-06-05 | 2017-06-09 | Michelle |  |  |  | Use same file from LatAm
| Purchse Org ? | 5d | 2017-06-05 | 2017-06-09 | Michelle |  |  |  | Use same file from LatAm
| Company Code ? - Metadata update by Sumit for Country | 5d | 2017-06-05 | 2017-06-09 | Michelle |  |  |  | Use same file from LatAm
| Event Configurations | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Event Configuration Countries | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Event Layouts | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Event Actions | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Event Rules | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Expense Types ? | 5d | 2017-06-05 | 2017-06-09 | Veeva
TRUE | Evergreen MSA Topic Creation and Sharing | 2d | 2017-06-10 | 2017-06-11 | Veeva
| Demo/Test training Topic creation? - not required | 5d | 2017-06-05 | 2017-06-09 | Veeva
| Sign In Sheets (Topics + Attachment) for BE, NL, UK/IR | 5d | 2017-06-05 | 2017-06-09 | Veeva
TRUE | User Preferences records for CRM Users (During Blackout) | 2d | 2017-06-10 | 2017-06-11 | Sumit
TRUE | User Preferences records for EM Only users - needs data from Business | 2d |  |  | Veeva
| Service Providers ? Confirm with Business | 2d |  |  | Veeva
TRUE | New/Updated Veeva Messages |  |  |  | Veeva
TRUE | Veeva Messages update to remove old verbiage - Activity, Need etc |  |  |  | Veeva
| Non DOCT Payees ? To be loaded manually by SCs | 2d |  |  | n/a
| DOCT Payees - Loading only DOCT via the interface | 2d |  |  | Michelle
TRUE | Deployment Verification Steps | 7d | 2017-06-05 | 2017-06-11
| Verify Issue Tracker Fixes | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Verify replacement of old verbiage in Veeva messages | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Verify labels and translations | 7d | 2017-06-05 | 2017-06-11 | Veeva |  |  |  | Double check include translations
| Verify Recordtype Defaults are set at Profile levels | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Ensure Expense Header FLS is removed from Profiles | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Ensure Page layout assignments are appropriate | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Ensure Preference record ownership and attributes are correct | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Ensure Custom Settings are set correctly | 7d | 2017-06-05 | 2017-06-11 | Veeva |  |  |  | May need to manually activate the Need approval process?
| Ensure iPad users work as design | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Ensure Germany users see expected screens online and on iPad | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Ensure No Access to Contacts | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Unit Testing | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Clear Cache + Refresh Config Console! | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Reset Passwords for new users | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Sync up English & other language translations | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Assign all EM Permission sets to vadmin and any Admin user that you use to refresh "Event Configuration Console" | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Cross check against BMS Global EM Deployment Plan (under Attachments tab) | 7d | 2017-06-05 | 2017-06-11 | Veeva
| Preferences - extract existing and upsert based on Preference record Id | 7d | 2017-06-05 | 2017-06-11 | Veeva
TRUE | Veeva Messages | 7d | 2017-06-05 | 2017-06-11 | Veeva
TRUE | Business User verification - Jun 11 SUNDAY Noon EST | 1d | 2017-06-11 | 2017-06-11 | Michelle
| Migration - Templates | 7d | 2017-06-05 | 2017-06-11
| Sign In Sheet | 7d | 2017-06-05 | 2017-06-11 | Veeva
| UKI Sign-In Sheet | 7d | 2017-06-05 | 2017-06-11
| UKI Sign-In Sheet Attendee | 7d | 2017-06-05 | 2017-06-11
| UKI Sign-In Sheet Blank | 7d | 2017-06-05 | 2017-06-11
| BE Sign-In Sheet | 7d | 2017-06-05 | 2017-06-11
| BE Sign-In Sheet Attendee | 7d | 2017-06-05 | 2017-06-11
| BE Sign-In Sheet Blank | 7d | 2017-06-05 | 2017-06-11
| NL Sign-In Sheet | 7d | 2017-06-05 | 2017-06-11
| NL Sign-In Sheet Attendee | 7d | 2017-06-05 | 2017-06-11
| NL Sign-In Sheet Blank | 7d | 2017-06-05 | 2017-06-11
| Migration - Integration | 7d | 2017-06-05 | 2017-06-11
| Vitalize Ticket for Informatica Changes | 5d | 2017-06-05 | 2017-06-09 | Sumit
| Informatica - EU | 1d | 2017-06-09 | 2017-06-09 | Sumit
| Informatica - LATAM | 1d | 2017-06-09 | 2017-06-09 | Sumit
| webMethods & MFT changes |  |  |  | Sumit
| Lanyon Changes |  |  |  | Fabien
TRUE | Assign Permissions/job to Production | 3d | 2017-06-09 | 2017-06-11 | Sumit |  |  |  | manual
| Log Tickets to SAP for Vendor PO and Payment Filters to include UKI+BLX | 3d |  |  | Michelle |  |  |  | manual
Final Tasks
User Setup
| Add New EM Only users | 1d |  |  | Veeva |  |  |  | Manual Setup. Ensure SCs have all permission sets aligned (8 total)
| Ariba Setup | 10d |  |  | Michelle
| SAP Setup | 10d |  |  | Michelle
| Schedule Informatica Jobs | 1d |  |  | Josephine

## Comments
Row 3 | Attach documents relevant to the task Save task related comments inside the sheet, on the task. Great for capturing emails, team notes and quick ideas. You can also attach documents or links to web pages directly to a discussion. | Alex Boit | 01/06/14 1:49 PM