## Slide 1
Global HCP,
Meetings & Congresses
April, 2017
InterAct Events Management 2.0

## Slide 2: InterAct EM 2.0 Scope
Simplified Tool to support simplified processes
  Flexible to support market simplification initiatives
Utilizing Core Veeva Out-of-the-box functionality
  Reduces support and maintenance costs
  Reduces EM screens from 92 to 6
Markets in Scope
  Initial 12 for 2017- early 2018
  InterCon & remaining markets timeline being confirmed

## Slide 3: InterAct EM 2.0 Status
Business Requirements Complete
System Integration Testing in process
Core Training Materials being finalized
Roll-out Planning in process
User Functionality Testing being planned

## Slide 4
InterAct EM 2.0 High Level Timeline
2017
2018
Today
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2018
Feb
Mar
EM 1.x Retest for Germany
Benelux
UK/Ireland
Nordics
Brazil
France
Italy
CHAT
Spain
Australia
Canada
Germany
Japan
37.4 days
EM 2.0 System Testing
19.4 days
EM 2.0 UAT
37.4 days
EM 2.0 Training Development

## Slide 5
2017
2017
Today
Week 1
3
5
7
9
11
13
40 days
Market Change Management
15 days
Market completes go-live plan
15 days
Market translates system & training materials if applicable
15 days
Market localization of training materials to market specific process
15 days
Data prep
5 days
System prep for testing
5 days
System Testing
5 days
Business Verification
10 days
System prep for go-live
5 days
Training
System Live
Market Implementation Timeline
HCP Projects team will work with market points to define specific timelines and deliverables.
25 days
Stabilization

## Slide 6
2017
2017
Today
Mar
Apr
May
Jun
Jul
Mar 20 - May 2
32 days
Build
Mar 20 - Jun 8
59 days
System Testing
Mar 20 - Apr 14
20 days
Develop SIT test plan & use cases
May 3 - Jun 2
23 days
Execute EM 2.0 SIT testing (incl. CRM regression)
Apr 12 - Jun 2
38 days
Germany UFT / Regression testing
Apr 10 - May 26
35 days
Training System Readiness
1 day
May 12
Training System Ready to be used
Apr 10 - May 19
30 days
Training Courseware Development
Apr 4 - Apr 24
15 days
Provide starter data for SIT testing
1 day
Jun 1
Deliver production ready business dataset
1 day
May 12
HCP Process Confirmation
Apr 17 - May 19
25 days
UFT Preparation
May 8 - May 17
8 days
UFT Logistics
Apr 17 - Apr 28
10 days
Develop UFT Use case Scenarios
May 3 - May 19
13 days
Test Script Prep
May 22 - Jun 2
10 days
UFT Execution
Apr 10 - Apr 21
10 days
Confirm Market Training Plan
May 3 - May 19
13 days
Localize training materials
Apr 21 - May 30
28 days
Training Scheduling and Logistics
5 days
May 31 - Jun 6
Train the Trainer
5 days
Jun 7 - Jun 13
Trainer Prep
May 30 - Jun 20
16 days
Deliver User training
5 days
Jun 5 - Jun 9
PTP activities
1 day
Jun 12
Go Live
Jun 15 - Jul 19
25 days
HyperCare Period
InterAct EM 2 Timeline – Benelux & UK

## Slide 7
2017
2017
Today
Jun
Jul
Aug
Sep
Jul 17 - Jul 28
10 days
System build/ test
Jun 29 - Jul 12
10 days
Core UFT Activities
Jun 28 - Jul 14
13 days
Provide starter data for SIT testing
Aug 1 - Aug 8
6 days
Deliver production ready business dataset
Jul 13 - Jul 24
8 days
UFT Logistics
1 day
Jul 13
Demo Core Scripts to GPO Leads
Jul 17 - Jul 28
10 days
Test Script Prep
5 days
Aug 3 - Aug 9
UFT Execution
Jun 15 - Jun 26
8 days
Confirm Market Training Plan
Jun 15 - Jun 30
12 days
Localize training materials
Jul 3 - Jul 21
15 days
Final updates incorporating localization
Jun 27 - Jul 24
20 days
Training Scheduling and Logistics
5 days
Jul 24 - Jul 28
Train the Trainer
Jul 31 - Aug 11
10 days
Trainer Prep
5 days
Aug 14 - Aug 18
Deliver User training
Jul 6 - Aug 21
33 days
Execute Communications & CM plan
5 days
Aug 10 - Aug 16
Data Load
3 days
Aug 17 - Aug 21
PTP
1 day
Aug 21
Nordics - Go Live
Aug 21 - Sep 1
10 days
HyperCare Period
InterAct EM 2 Timeline - Nordics

## Slide 8
2017
2017
Today
Jun
Jul
Aug
Sep
Aug 14 - Aug 25
10 days
System build/ test
5 days
Jul 10 - Jul 14
Provide to market fields to be translated
Jul 27 - Aug 9
10 days
Core UFT Activities
Jul 31 - Aug 11
10 days
Provide starter data for SIT testing
5 days
Aug 21 - Aug 25
Provide Business data refresh
Jul 17 - Aug 4
15 days
Translate all system required fields
Aug 29 - Sep 6
7 days
Deliver production ready business dataset
Aug 10 - Aug 21
8 days
UFT Logistics
Jul 27 - Aug 8
9 days
Develop UFT Use case Scenarios
Aug 11 - Aug 24
10 days
Test Script Prep
5 days
Aug 31 - Sep 6
UFT Execution
Jun 12 - Jun 22
9 days
Confirm Market Training Plan
Jun 12 - Jun 23
10 days
Localize training materials
Jul 17 - Aug 1
12 days
Translation of training materials
Aug 2 - Aug 18
13 days
Fianlize Training materials
Jun 22 - Aug 28
48 days
Training Scheduling and Logistics
5 days
Aug 21 - Aug 25
Train the Trainer
Aug 28 - Sep 8
10 days
Trainer Prep
5 days
Sep 11 - Sep 15
Deliver User training
Aug 14 - Sep 22
30 days
Execute Communications & change management plan
5 days
Sep 7 - Sep 13
Data Load
2 days
Sep 14 - Sep 15
PTP
1 day
Sep 18
Wave 3 - Go Live
Sep 18 - Sep 29
10 days
HyperCare Period
InterAct EM 2.0 Timeline - Spain

## Slide 9
2017
2017
Today
May
Jun
Jul
Aug
3 days
Jun 15 - Jun 19
Provide to market fields to be translated
Jun 12 - Jun 23
10 days
Set up new Org
Jun 26 - Jul 14
15 days
System build/ test (incl. EM 1.x regression)
Jun 5 - Jun 16
10 days
Provide starter data for SIT testing
5 days
Jul 14 - Jul 20
Deliver production ready business dataset
Jun 20 - Jun 30
9 days
Translate all required fields
Jun 26 - Jul 5
8 days
UFT Logistics
3 days
Jun 21 - Jun 23
Prep UFT Environment (including data prep)
Jun 28 - Jul 14
13 days
Test Script Prep
5 days
Jul 17 - Jul 21
UFT Execution (incl. EM 1.x regression)
May 25 - Jun 6
9 days
Confirm Market Training Plan
May 25 - Jun 7
10 days
Localize training materials
Jun 8 - Jun 20
9 days
Final updates incorporating localization
Jun 21 - Jun 30
8 days
Translation of training materials
Jul 3 - Jul 11
7 days
Finalize training materials
Jun 6 - Jul 17
30 days
Training Scheduling and Logistics
5 days
Jul 12 - Jul 18
Train the Trainer
Jul 19 - Jul 28
8 days
Trainer Prep
Jul 31 - Aug 11
10 days
Deliver User training
Jun 5 - Jun 16
10 days
Confirm Market CM & Comm plan
Jun 19 - Aug 4
35 days
Execute Communications & CM plan
5 days
Jul 24 - Jul 28
Data Load
Jul 31 - Aug 7
6 days
PTP
1 day
Aug 7
Brazil - Go Live
Aug 7 - Aug 25
15 days
HyperCare Period
InterAct EM 2.0 Timeline - Brazil

## Slide 10
2017
2017
Today
Jun
Jul
Aug
Sep
Oct
Aug 14 - Aug 25
10 days
System Build/Test
5 days
Jul 3 - Jul 7
Provide file for translation
Jul 24 - Aug 4
10 days
Provide starter data for SIT testing
5 days
Aug 14 - Aug 18
Provide Business data refresh
6 days
Aug 28 - Sep 4
Deliver production ready business dataset
Jul 25 - Aug 7
10 days
Core UFT Activities
Jul 10 - Jul 21
10 days
Translate all required fields
Aug 10 - Aug 21
8 days
UFT Logistics
Aug 11 - Aug 24
10 days
Test Script Prep
Aug 29 - Sep 13
12 days
UFT Execution
1 day
Jun 21
Training: data staging
Jun 14 - Jun 27
10 days
Localize training materials
Jul 10 - Jul 21
10 days
Translation of training materials
Aug 2 - Aug 18
13 days
Fianlize Training materials
3 days
Aug 23 - Aug 25
Train the Trainer
6 days
Aug 28 - Sep 4
Trainer Prep
Sep 6 - Sep 22
13 days
Deliver User training
Jun 22 - Sep 28
71 days
Execute Communications & change management plan
5 days
Sep 14 - Sep 20
Data Load
2 days
Sep 21 - Sep 22
PTP
1 day
Sep 25
Italy - Go Live
Sep 25 - Oct 6
10 days
HyperCare Period
InterAct EM 2 Timeline - Italy

## Slide 11
2017
2017
Today
Jul
Aug
Sep
Oct
Nov
Aug 7 - Aug 18
10 days
Set up new Org
Aug 21 - Sep 8
15 days
System build/ test
Aug 14 - Sep 1
15 days
Translate all system required fields
Aug 7 - Aug 18
10 days
Provide starter data for SIT testing
5 days
Sep 21 - Sep 27
Deliver production ready business dataset
5 days
Aug 7 - Aug 11
Provide market fields for translation
Aug 11 - Aug 24
10 days
Core UFT Activities
Aug 25 - Sep 5
8 days
UFT Logistics
Aug 29 - Sep 14
13 days
Test Script Prep
Sep 15 - Sep 28
10 days
UFT Execution (incl. EM 1.x regression)
Jul 19 - Jul 31
9 days
Confirm Market Training Plan
Jul 19 - Aug 4
13 days
Localize training materials
Aug 7 - Aug 18
10 days
Final updates incorporating localization
Aug 21 - Sep 5
12 days
Translation of training materials
Sep 6 - Sep 15
8 days
Finalize training materials
Aug 1 - Sep 25
40 days
Training Scheduling and Logistics
5 days
Sep 18 - Sep 22
Train the Trainer
Sep 25 - Oct 6
10 days
Trainer Prep
5 days
Oct 9 - Oct 13
Deliver User training
Aug 21 - Oct 13
40 days
Execute Communications & CM plan
5 days
Sep 29 - Oct 5
Data Load
6 days
Oct 6 - Oct 13
PTP
1 day
Oct 16
Canada - Go Live
Oct 16 - Nov 3
15 days
HyperCare Period
InterAct EM 2.0 Timeline - Canada

## Slide 12
Old Slides

## Slide 13
2017
2017
Today
May
Jun
Jul
Aug
Sep
5 days
Jun 12 - Jun 16
Provide market fields that may need to be translated
Jun 12 - Jun 23
10 days
Set up new Org
Jun 26 - Jul 14
15 days
System build/ test
Jun 12 - Jun 23
10 days
Provide starter data for EU full for SIT testing
Jun 19 - Jul 7
15 days
Translate all required fields
5 days
Jul 28 - Aug 3
Deliver production ready business dataset
Jun 19 - Jun 30
10 days
Core UFT Activities
Jul 3 - Jul 12
8 days
UFT Logistics
Jul 5 - Jul 21
13 days
Test Script Prep
Jul 24 - Aug 4
10 days
UFT Execution
May 24 - Jun 5
9 days
Confirm Market Training Plan
May 24 - Jun 9
13 days
Localize training materials
Jun 12 - Jun 23
10 days
Final updates incorporating localization
Jun 26 - Jul 11
12 days
Translation of training materials
Jul 12 - Jul 21
8 days
Finalize training materials
Jun 5 - Jul 31
41 days
Training Scheduling and Logistics
5 days
Jul 24 - Jul 28
Train the Trainer
Jul 31 - Aug 11
10 days
Trainer Prep
5 days
Aug 14 - Aug 18
Deliver User training
Jun 12 - Jun 23
10 days
Confirm Market CM & Comm plan
Jun 26 - Aug 18
40 days
Execute Communications & CM plan
5 days
Aug 7 - Aug 11
Data Load
6 days
Aug 14 - Aug 21
PTP
1 day
Aug 21
Brazil - Go Live
Aug 21 - Sep 8
15 days
HyperCare Period
InterAct EM 2.0 Timeline – Brazil (Old)